## Sheet1
AUDIT CHALLENGE FY19/20 & FY20-21 EXTERNAL AUDITORS COMMENTS/ RECOMMENDATIONS ACTION PLAN As At 18 May 22
Ser | Comment/ Recommendations | Action required | Lead | Due date | Status | Remarks
(a) | (b) |  | (c) | (d) | (e) | (f)
1 | Post copy of External Auditors Letter RP/SAAA/WI0187 of 26 Apr 22 on Website | Resolution madeb at PC held on 128 Maty 22 to publish on website | RFO | 20May 22 | Pending
2 | Council responds ‘No’ to Assertion 4 of the 2021/22 Annual Governance Statement. | Resolution made at 18 May PC Meeting and Amend statement to be published on website | RFO | 28 June 22 | Pending
3 | Council to ensure that it makes proper provision for the exercise of public rights during 2022/23. | Resolution made at PC Meeting held on 18 May 22 to set the dates notice of the exercise of public rights as 30 Jne to 11 Aug 22 | RFO & F&A and Governance Committees | to be posted by 29 Jun to meet displayed of 30 Jun - 11 Aug | Pending
4 | Council responds ‘No’ to Assertion 4 of the 2021/22 Annual Governance Statement. | Resolution to at 18 May PC Meeting and Amend statement to be published on website | Governance Committee | 28 June 22 | Pending
5 | Council website not complying with transparency code for parish councils or the Council not complying with Freedom of Information Act 2000 a. Publication scheme – out of date and contains errors. b. Other out of date documents, e.g. various Council policies, Standing Orders and Financial Regulations. c. Documents containing known errors should be corrected, e.g. payments over £100 during 2020/21 d. Budget setting and monitoring documentation, including consideration and approval of earmarked reserves. e. Agenda papers – publication of non-confidential papers with the agendas. f. Register of interests – should be on website, not just linked to Wiltshire Council website. | a. Publication scheme – update and correct errors. b Council policies,, Standing Orders and Financial Regulations update, adopt and publish on website. c. Correct know errors ,add £9K payment. d. Publish Budget setting and monitoring documentation, including consideration and approval of earmarked reserves. e. Agenda papers – publish non-confidential papers with the agendas. f. Register of interests – to be on website, not just linked to Wiltshire Council website. | RFO & F&A and Governance Committees | a. 1 Nov 22 B. Adopted on 18 May 22 to be displayed on 20 mMy 22 c. 1 Nov 22 d. 1 Jun 22 e. With effect from May 22 PC Mtg f. 1 Nov 22 | a. On agenda for 18 May meeting b. Pending c. Pending d .Pending e. Pending f. Pending
6 | It is recommended that the Council’s agendas and minutes should appropriately record the powers used and the resolutions made during meetings, in particular the appropriate approval of spending decisions and payments made by the Council. | record the powers used and the resolutions made during meetings, in particular the appropriate approval of spending decisions and payments made by the Council. | RFO/Clerk | With Effect from 18 May PC Mtg | Pending
7 | It is recommended that the Council continues to seek written clarification of the historic VAT issue regarding a VAT reclaim for work carried out on county council owned pavement from issue regarding a VAT reclaim for work carried out on county council owned pavement from HMRC. | The Council has written to HMRC at ?????? And is awaiting a reply | RFO |  | Pending
8 | It is recommended that the Council liaise with the local association to ensure that appropriate training is provided for all Members and employees. | Contact County Secretary at WALC | Chairman & Clerk | By 1 Jun for training to be arranged ASP | Pending
9 | It is recommended that the Council considers the cost/benefit of submitting an AGAR for limited assurance review by the appointed auditor rather than certifying exemption from the review for 2021/22. | Consider the cost/benefits of not certifying from exemption | RFO & Cllrs | Consider at May 22 PC Mtg | Pending
10 | It is recommended that the Council uses the mandatory requirements listed in Section 1 of the JPAG Practitioners’ Guide as a checklist for each response to the Annual Governance Statement assertions in future in order to frame the consideration of responses. | Interrogate Guide and use the mandatory requirements listed in Section 1 JPAG Practitioners’ Guide as a checklist | RFO and F&A Committee | Use for 21/22 AGAR | Pending
11 | It is recommended that, in view of the recently received comments about the Council’s financial records, the Council establishes an accurate baseline for its financial accounts as at 1 April 2021 and then maintains adequate financial records going forwards. These should be reviewed by the Council on a quarterly basis, including reconciliations of all bank accounts. | Accurate Bassline & bank Reconciliation to be established as at 1 April 21. | RFO and F&A Committee | Baseline presented at 18 May 22 PC Mtg with Bank Reconciliations presented at every PC Mtg. Accts to be reviewed Quarterly from 1 Jul 22 | Pending